## samity
| Project Name: | MRA-IMS
| Feature Name: | Samity
Reference Document:
| Created By: | Md Asaduzzaman / Sabina Yeasmin
Reviewed By:
| Date of Creation: | 2023-05-09
Date of Review:
| Number of cases: | 10
# | TEST CASE ID | TEST CASE | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | Developer Status | Developer Name | RETESTING STATUS | Retester Name
1 | samity-01 | Verify Samity List Page. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. |  | Will see the "Samity List" page. | Showing the "Samity List" page. | Passed
2 | samity-02 | Verify switching Language( Bangla to english). | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on 'English'. |  | Every text will translate into english. | Every text is showing in English. | Passed
3 | samity-3 | Verify searching in placeholder. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Type in the search by (Name, Status). | Search Name: Palli Progoti Sahayak Samitee (PPSS) | The "Palli Progoti Sahayak Samitee (PPSS)" name will be displayed in samity list. | The name "Palli Progoti Sahayak Samitee (PPSS)" is displayed in the samity list. | Passed
4 | samity-4 | Verify the Samity Filtering by Status. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on "Select Status" dropdown and select status(Active, Inactive Or All). | Select Status: All/Active/Inactive | The Samities will be shown according to the status selected from the status dropdown. | The Samities has been showing according to the status selected from the status dropdown. | Passed
5 | samity-5 | Verify the Samity Filtering by Branch. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on 'Select Branch' dropdown and select any branch. | Select Branch:Comilla Branch | The branch which is selected, will be seen in the list of samity of that branch. | The branch which is selected is seen in the list of samity of that branch. | Passed
6 | samity-6 | Verify the lock Samity(s) from Samity List. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3.Click on action "Lock" icon button. | Lock Samity: Palli Progoti Sahayak Samitee (PPSS) | Selected lock samity "Palli Progoti Sahayak Samitee (PPSS)" will be locked and no one can lock again. | Locked "Palli Progoti Sahayak Samitee (PPSS)" Samity list. | Passed
7 | samity-7 | Verify the unlock Samity(s) from Samity List. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3.Click on action "Unlock" icon button. | Unlock Samity: Palli Progoti Sahayak Samitee (PPSS) | Selected unlock samity "Palli Progoti Sahayak Samitee (PPSS)" will be unlocked. | Unlocked "Palli Progoti Sahayak Samitee (PPSS)" Samity list. | Passed
8 | samity-8 | Verify Edit feature of Samity. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on Action "Edit" icon button of any 'samity name' list. | Edit Samity Name: Palli Progoti Sahayak Samitee (PPSS). | "Palli Progoti Sahayak Samitee (PPSS)" can be edited. | "Palli Progoti Sahayak Samitee (PPSS)" is being edited. | Passed
9 | samity-9 | Verify View Feature of Samity. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on Action "View" icon button of any 'samity name' list. | View Samity Name: Palli Progoti Sahayak Samitee (PPSS). | "Palli Progoti Sahayak Samitee (PPSS)" name detail will be displayed. | "Palli Progoti Sahayak Samitee (PPSS)" name detail are displayed. | Passed
10 | samity-10 | Verify Create Samity with correct data. | 1. User must have a browser and internet connection. 2. User must be logged in. 3. Language should be in English. | 1. Click on 'Samity' from the left side menu. 2. Click on 'Samity'. 3. Click on"Create samity" 4. Type the correct data in all the placeholders of the Add samity page. 5. Click on "Save data" | 1. Name(English):Feni Samity(FS) 2. Name(Bangla):ফেনী সমিতি (এফএস) 3. Center Type: Monthly 4. Center Time:12 5. Samity Code:SAM-C-0010 6. Registration No:054389 7. Branch: Chhagalnaiya Branch 8. Maximum Numbe:20 9. Total Member:20 10. Total Borrower:20 11. Collection Date:5/7/2023 12. Opening Date:5/8/2023 13. Samity Type:Weekly 14. Collection Type:Regular 15. Samity Day:Tuesday 16. Recoverable Week:1st week 17. Is Samity Day Optional:Day 18. Is Samity Day Optional :no 19. Is Transfer:no 20. Location :Adabor 21. Working Area:Active 22. Address English:Mohammadpur 23. Address Bangla:মোহাম্মদপুর 24. Remarks:Done | New Samity will be created with correct data. | New Samity created with correct data. | Passed